## Instructions-Summary
Instructions | BU
1. Complete the Summary Table to the Right of this line. | Team
2. Complete the Users Worksheet for Users You Want to Provide Access to the DR Tracker | App Owner
3. Complete the Data Values Worksheet | Lead PM
4. Review the HxH Plan Template Guide. You need to a template to create an Hour By Hour Plan. | Test Timing (Month/Year)
5. Populate the Failover/Failback Plan Worksheet with your finalized Plan for this year.
6. Populate the Data Corruption HxH Plan Worksheet with your finalized Plan for this year.
7. In order to migrate all of this information to the DR Tracker Database, I would need to have this spreadsheet ready to go 6 weeks before your test date.

## Users
WK E-mail Address | User Type

## Data Values
Application Names | Components (i.e. App VM, Oracle DB, SQL Server DB, CaaS Container) | Any Other Environments? (Default: Dev, QA, Stage and Prod) | Any Other Hosting Sites? (Default: AWS Virginia, AWS Ohio, AWS Oregon, Azure Iowa)

## HxH template Guide
Available Columns
Test Type | FO/FB or Data Corruption | See Example Screenshot. Rows in Blue are Header Rows. Rows in White are Detail Rows
BU | i.e. TAA/L&R, Health, FCC, Corp, etc
BU Team | i.e. Advantage Ecosystem
Row ID | Autoincrement From 1
Row Type | 0= Header, 1= Detail
Application Name
Section (i.e. AVP) | For DR Start Declaration use 5585, For ARP Completion Use 5590, For App Dataysnch completion, please use 5620, For App Dataysnch completion, please use 5630
Task Description
Task Details
Team
Assigned Resource(s)
Duration (In Minutes)
Predecessor Task(s) Row ID | Can Comma Separate 5,8 For More Than 1 Predecessor

## Failover-Failback HxH plan
| Test Type | BU | BU Team | Row ID (Autonumber) | Row Type (0 = Header Or 1 = Detail) | Application Name | Component | Section (e.g. AVP) | Task Description | Task Details | Jira/RITM Reference | Team Name (i.e. Health QA) | Assigned Resource(s) | Duration (In Minutes) | Predecessor Task Row ID(s)
Sample Row | FO/FB | Health | Advantage Ecosystem | 1 | 0 | IIB |  | AVP | Conduct Pre-Test AVP | Login User ID: testlogin |  | Health QA | Devon Manelski, Elena Kalymokova | 60 | 0
Sample Row | FO/FB | Health | Advantage Ecosystem | 2 | 1 | Advantage |  | AVP | Conduct Pre-Test AVP |  | WKHL-1234 | Health QA | Devon Manelski | 30 | 1
Sample Row | FO/FB | Health | Advantage Ecosystem | 3 | 1 | Advantage |  | AVP | Conduct Pre-Test EDI AVP |  | WKHL-1234 | Health QA | Devon Manelski | 30 | 1,2

## Data Corruption HxH
| Test Type | BU | BU Team | Row ID (Autonumber) | Row Type (0 = Header Or 1 = Detail) | Application Name | Component | Section (e.g. AVP) | Task Description | Task Details | Jira/RITM Reference | Team Name (i.e. Health QA) | Assigned Resource(s) | Duration (In Minutes) | Predecessor Task Row ID(s)
Sample Row | Data Corruption | Health | Advantage Ecosystem | 1 | 0 | IIB |  | AVP | Conduct Pre-Test AVP | Login User ID: testlogin |  | Health QA | Devon Manelski, Elena Kalymokova | 60 | 0
Sample Row | Data Corruption | Health | Advantage Ecosystem | 2 | 1 | Advantage |  | AVP | Conduct Pre-Test AVP |  | WKHL-1234 | Health QA | Devon Manelski | 30 | 1

## Lookups (hidden)
BU | User Type
Health | Standard
FCC | PM/App Owner
Corp | Admin
TAA/L&R